## Sheet1
Date | Attendance | Location | Topics Discussed | Goals | Ideas | Timeline
2.16.19 | All Present | Discord | - getting environment setup - Milestone 1 topics | Next Meeting Up For Discussion: - Milestone 1
2.18.19 | All Present | CASE Building | -Login page ideas -Big Picture Ideas -Name -Milestone 1 collaboration | Next Meeting Up For Discussion: -Meet Discord 11am
2.23.19 | All Present minus 2 people | Discord | - content: Logo, Slogan, Pictures, directory - Scope of App is Boulder City Limits - Include these sports: Tennis, Basketball, Soccer, Football, Disc Golf, Ult. Frisbee - Allow for user: Declare/propose field/location/sport - collect pictures of locations - Possible Calendar portion - Google map connection VS static maps - After each code segment test on Androir and IOS - Figure IOS testing - Data sets from Google dataset - Start to figure out breakdown of timeline - user data collection - google login - registration/login/about on website - form groups of 2 or 3 for each task, if difficult, increase people on task - possible frontend host on google sites, ask TA opinion on how to have free website that is functional for app - Use Firestore as a backend to Flutter app? - Google Sites, Google Firestore, Google Datasets, Google Sheets - sports browser possibility | Next Meeting Up For Discussion: - Meet Discord 11am - Determine realistic Agile/Scrum outline - Determine iteration timelines - Determine type of "deliverables" - Check out Asuana for flow sheet
2.25.19 |  |  | -
3.2.19
3.4.19
3.9.19
3.11.19
3.16.19
3.18.19
3.23.19
3.25.19
3.30.19
4.1.19